## Sheet1
Week | Day | Date | Completed work
Week1 | Monday | 2019-09-16 | Find members
| Tuesday | 2019-09-17 | Find members
| Wednesday | 2019-09-18 | Find members
| Thursday | 2019-09-19 | Find members
| Friday | 2019-09-20 | Find members
| Saturday | 2019-09-21 | Find members
| Sunday | 2019-09-22 | Find members
Week2 | Monday | 2019-09-23 | Discuss topic with members
| Tuesday | 2019-09-24 | Discuss topic with members
| Wednesday | 2019-09-25 | Topic background search
| Thursday | 2019-09-26 | Topic background search
| Friday | 2019-09-27 | Make a decision about topics with team. The selected topic is topic 6(Stock Management System).
| Saturday | 2019-09-28 | Read some reference about topic 6.
| Sunday | 2019-09-29 | Team members rebel, they want to change the topic. Discussing whole day.
Week3 | Monday | 2019-09-30 | Make a new decision about topics with team.The selected topic is topic 3(Double robotic application development).
| Tuesday | 2019-10-01 | Double robotic background research.
| Wednesday | 2019-10-02 | The first time we meet with Double robotic and connect it with iphone.
| Thursday | 2019-10-03 | Team members argue the feasibility of our robotic plan. Arguing whole day again.
| Friday | 2019-10-04 | Checking the functions of Double robotic.
| Saturday | 2019-10-05 | Giving up the topic 3. The version of Double robotic is 2.0 which is totally different from the Double 3(The last version).
| Sunday | 2019-10-06 | A new plan on topic 6. We will focus on the foreign exchange trade system design.
Week4 | Monday | 2019-10-07 | Writing proposal of topic 6.
| Tuesday | 2019-10-08 | Task assignment of topic 6. I will complete the database, analysis and prediction parts.
| Wednesday | 2019-10-09 | Database fucntion design. Data collection.
| Thursday | 2019-10-10 | Database coding.
| Friday | 2019-10-11 | Database coding.
| Saturday | 2019-10-12 | Database coding.
| Sunday | 2019-10-13 | Database coding.
Week5 | Monday | 2019-10-14
| Tuesday | 2019-10-15
| Wednesday | 2019-10-16
| Thursday | 2019-10-17
| Friday | 2019-10-18
| Saturday | 2019-10-19
| Sunday | 2019-10-20
Week6 | Monday | 2019-10-21
| Tuesday | 2019-10-22
| Wednesday | 2019-10-23
| Thursday | 2019-10-24
| Friday | 2019-10-25
| Saturday | 2019-10-26
| Sunday | 2019-10-27
Week7 | Monday | 2019-10-28
| Tuesday | 2019-10-29
| Wednesday | 2019-10-30
| Thursday | 2019-10-31
| Friday | 2019-11-01
| Saturday | 2019-11-02
| Sunday | 2019-11-03
Week8 | Monday | 2019-11-04
| Tuesday | 2019-11-05
| Wednesday | 2019-11-06
| Thursday | 2019-11-07
| Friday | 2019-11-08
| Saturday | 2019-11-09
| Sunday | 2019-11-10
Week9 | Monday | 2019-11-11
| Tuesday | 2019-11-12
| Wednesday | 2019-11-13
| Thursday | 2019-11-14
| Friday | 2019-11-15
| Saturday | 2019-11-16
| Sunday | 2019-11-17
Week10 | Monday | 2019-11-18
| Tuesday | 2019-11-19
| Wednesday | 2019-11-20
| Thursday | 2019-11-21
| Friday | 2019-11-22
| Saturday | 2019-11-23
| Sunday | 2019-11-24